## empty
Incident ID | Focus List | Site ID | Incident Status | Planning Prep Start/End/Within | Emergency | Approver | Estimated Implementation Start | Estimated Implementation End | Estimated Downtime (mins) | Synopsis | Coordinator | Collaborator | Next Action Owner
VECJ9VNWV |  | DISCOVER42 | Approved With Comments | (No planning/prep window) | No | Akhilesh Kasarla | 2020-04-13 20:30:00 | 2020-04-13 22:30:00 | 0 | CMIC Upgrade - From 14.00.05.00 to 14.02.01.00 | Kapil Kapil | Bhargavi Mariyala Keith Boggs | Kapil Kapil
VECHMS4CM |  | DISCOVER40 | Approved With Comments | (No planning/prep window) | Yes | Steve Lechleiter | 2020-04-18 18:00:00 | 2020-04-18 20:30:00 | 130 | Firmware - FRO3665 Flash all NetApp Snowmass controllers (2660) to controller FW 08.20.30.30 from 07.86.52.30 (outage needed) | Kapil Kapil | Keith Boggs Puneet Sharma | Kapil Kapil
VECJ9GHGB | Y Y | BOFAVA16 | Approval Pending | 2020-04-04 20:30:00 2020-04-18 16:30:00 2020-04-07 20:30:00 2020-04-18 20:30:00 Past window | No | Akhilesh Kasarla | 2020-04-18 20:30:00 | 2020-04-19 00:30:00 | 0 | OS Patch - Security Bundle - VM SWS using 02/xx/2020 bundle(20200203-1) | Kapil Kapil | Praveena Veesam | Akhilesh Kasarla
VECJ9NKWX | Y Y | BOFAVA16 | Approval Pending | 2020-04-04 20:30:00 2020-04-18 16:30:00 2020-04-07 20:30:00 2020-04-18 20:30:00 Past window | No | Sunil Adepu | 2020-04-18 20:30:00 | 2020-04-19 00:30:00 | 0 | OS Patch - Security Bundle - Channel Node (smp990-14adppee, smp990-15adppee) (VECJ9GHJ5) using 02/xx/2020 bundle | Kapil Kapil |  | Sunil Adepu
VECJ9MKMX | Y | BOAV03TX1 | Approved With Comments | 2020-04-04 20:30:00 2020-04-18 16:30:00 2020-04-07 20:30:00 2020-04-18 20:30:00 Past window | No | Akhilesh Kasarla | 2020-04-18 20:30:00 | 2020-04-19 00:30:00 | 0 | Managed Server - OS Patch - Viewpoint - Security Bundle using the 02/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJA4RLM |  | RSADRTEST | Approved | (No planning/prep window) | No | James Presley | 2020-04-22 20:30:00 | 2020-04-24 22:30:00 | 0 | NPARC - From RSADRTEST 14.10.05.05 to TDICAMRSADEV01 16.20.43.01 | Kapil Kapil | Praveena Veesam Uduthalapally Alekya Aruna Paladugu Ryan Elder Bhargavi Mariyala Yesu Babu Meegada Robert Schwarz Rajesh Jakkula | Kapil Kapil
VECJ9DGG2 | Y Y | BOAD00TX18P11 | Approval Pending | 2020-04-09 19:30:00 2020-04-23 15:30:00 2020-04-12 19:30:00 2020-04-23 19:30:00 Past window | No | Akhilesh Kasarla | 2020-04-23 19:30:00 | 2020-04-23 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 02/14/2020 bundle | Kapil Kapil |  | Akhilesh Kasarla
VECJ9GHGG | Y Y | BOFATX18 | Approval Pending | 2020-04-09 19:30:00 2020-04-23 15:30:00 2020-04-12 19:30:00 2020-04-23 19:30:00 Past window | No | Akhilesh Kasarla | 2020-04-23 19:30:00 | 2020-04-23 23:30:00 | 0 | OS Patch - Security Bundle - VM SWS using 02/14/2020 bundle | Kapil Kapil |  | Akhilesh Kasarla
VECJ8L5YQ | Y | ESIPSTDWCERT | Approved With Comments | (No planning/prep window) | No | Akhilesh Kasarla | 2020-04-23 19:30:00 | 2020-04-23 21:30:00 | 120 | TD Patch Upgrade - from DBS/PDE 16.20.32.14 to DBS/PDE 16.20.43.01 using latest certlist and CVE bundle 2020-03-13 | Manasa Pola | Kapil Kapil | Manasa Pola
VECJ634NV |  | BIGLOTS8 | Discovery Complete | (No planning/prep window) | Yes | Michael Martin | 2020-04-24 04:31:00 | 2020-04-24 07:31:00 | 180 | OS Upgrade - from SLES11 SP1 to SLES11 SP3 (TPA 16.20.32.20 3+2) via certlist 10212019 | Kapil Kapil |  | Kapil Kapil
VECJB48E5 |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Paul Gray | 2020-04-24 23:30:00 | 2020-04-25 01:30:00 | 0 | CC - Firmware Upgrade Implement FRO 3691 or Microcode Array Controller (Flash all NetApp Soyuz controllers (5501) to controller FW 08.25.19.31 (or later).) | Kapil Kapil |  | Kapil Kapil
VECJ6QCWC |  | TELEMAR08 | Approval Pending | (No planning/prep window) | No | James Presley | 2020-04-25 17:30:00 | 2020-04-27 18:30:00 | 0 | CC - NPARC From Source TELEMAR08 (2690 4n) 14.10.07.10 to Target OI05 IFX 2.1 6+1 16.20.32.22-1 | Bhargavi Mariyala | Aruna Paladugu Riya Srivastava Kapil Kapil Manasa Pola Matt Moeller Lucas Alves Da Silva Ricardo Bueno Koshal Vyas Satish Pothula | James Presley
VECJBAAUQ |  | DISCOVER42 | Discovery Complete | (No planning/prep window) | Yes | Akhilesh Kasarla | 2020-04-26 03:30:00 | 2020-04-26 05:30:00 | 0 | Teradata Software Database upgrade - patch/efix From 16.10.04.02 to 16.10.06.03 to pick up DR 193643 | Kapil Kapil | Keith Boggs | Kapil Kapil
VECJ9GHHS | Y Y | BOFAVATMS00 | Discovery Complete | 2020-04-14 19:30:00 2020-04-28 15:30:00 2020-04-17 19:30:00 2020-04-28 19:30:00 1-5 days | No | Akhilesh Kasarla | 2020-04-28 19:30:00 | 2020-04-28 23:30:00 | 0 | OS Patch - Security Bundle - VM SWS using 02/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJA6SRR | Y | BOAD09VA2 | Discovery Complete | 2020-04-14 19:30:00 2020-04-28 15:30:00 2020-04-17 19:30:00 2020-04-28 19:30:00 1-5 days | No | Sunil Adepu | 2020-04-28 19:30:00 | 2020-04-28 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 02/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJB37XS |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Kevin Nelson | 2020-05-01 19:00:00 | 2020-05-01 21:30:00 | 0 | Viewpoint Upgrade - From 16.10.00.02 to 16.20.xx.xx | Kapil Kapil |  | Kapil Kapil
VECJAL27Y |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Sunil Adepu | 2020-05-01 21:30:00 | 2020-05-01 23:30:00 | 0 | Upgrade CMIC from 12.08.04.00 to 12.08.06.00 | Kapil Kapil |  | Kapil Kapil
VECJAL27X |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Sunil Adepu | 2020-05-01 22:30:00 | 2020-05-02 00:30:00 | 0 | Upgrade CMIC from 12.08.06.00 to 14.01.03.00 | Kapil Kapil |  | Kapil Kapil
VECJ76KGU |  | ANSESARG01 | Discovery Complete | (No planning/prep window) | No | Akhilesh Kasarla | 2020-05-02 03:30:00 | 2020-05-02 05:30:00 | 0 | Firmware - Teradata Upgrade TESA CMIC From 12.08.06.00 to 14.01.03.00 | Kapil Kapil |  | Kapil Kapil
VECJ76KGW |  | ANSESARG02 | Discovery Complete | (No planning/prep window) | No | Akhilesh Kasarla | 2020-05-02 03:30:00 | 2020-05-02 05:30:00 | 0 | Firmware - Teradata Upgrade TESA CMIC From 12.08.06.00 to 14.01.03.00 | Kapil Kapil |  | Kapil Kapil
VECJB89J9 |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Paul Gray | 2020-05-06 03:30:00 | 2020-05-06 05:30:00 | 0 | FIRMWARE Implement FRO_3692 Firmware or Microcode Array Controller | Kapil Kapil |  | Kapil Kapil
VECJA6SKL |  | DIXONS2800 | Approval Pending | (No planning/prep window) | No | Satoshi Nakamura | 2020-05-07 17:07:00 | 2020-05-07 19:07:00 | 0 | ICC P&I - 35FRO3669 Firmware or Microcode Array Controller | Kapil Kapil |  | Satoshi Nakamura
VECJA6SKR |  | DIXONS2800 | Approval Pending | (No planning/prep window) | No | Satoshi Nakamura | 2020-05-07 17:14:00 | 2020-05-07 19:14:00 | 0 | ICC Prep - 35FRO3676 Firmware or Microcode BIOS/Baseboard - TPA and Channel nodes | Kapil Kapil |  | Satoshi Nakamura
VECJA6SKT |  | DIXONS2800 | Approved | (No planning/prep window) | No | Lambert Ho | 2020-05-07 17:20:00 | 2020-05-07 19:20:00 | 0 | ICC Prep - 35FRO3685 Firmware or Microcode BIOS/Baseboard - BAR/NONTPA | Kapil Kapil |  | Kapil Kapil
VECJA6SL3 |  | DIXONS2800 | Approved | (No planning/prep window) | No | Lambert Ho | 2020-05-07 17:32:00 | 2020-05-07 19:32:00 | 0 | ICC Prep - 35FRO3670 Firmware or Microcode BIOS/Baseboard - BAR/NONTPA | Kapil Kapil |  | Kapil Kapil
VECHCQG58 |  | BANAGRARIO4 | Approved | (No planning/prep window) | No | Paul Gray | 2020-05-08 16:30:00 | 2020-05-08 20:30:00 | 240 | Minor Upgrade - from DBS/PDE 15.00.05.17 to DBS/PDE 15.10.06.04 or later [P&I] | Kapil Kapil |  | Kapil Kapil
VECHCQG5B |  | BANAGRARIO3 | Discovery Complete | (No planning/prep window) | No | James Presley | 2020-05-08 16:30:00 | 2020-05-08 20:30:00 | 240 | Minor Upgrade - from DBS/PDE 15.00.05.17 to DBS/PDE 15.10.06.04 [P&I] | Kapil Kapil |  | Kapil Kapil
VECJAJX4B |  | USM2 | Discovery Complete | (No planning/prep window) | No | Steve Lechleiter | 2020-05-09 04:30:00 | 2020-05-11 04:30:00 | 0 | NPARC - SEED migration from USM2 DBS/PDE 15.10.05.04 to TDCLOUDAZTDUSP1 DBS/PDE 16.20.xx.xx | Riya Srivastava | Anjani Kakkirala Puneet Sharma Vidya N Kapil Kapil P.Nikhil Reddy Vignesh Murugesan | Riya Srivastava
VECHR654P |  | COMPAR04 | Discovery Complete | (No planning/prep window) | No | Sunil Adepu | 2020-05-09 21:30:00 | 2020-05-10 00:30:00 | 0 | Firmware - VMS/CMIC Upgrade - from CMIC 11.06.04.00 to CMIC 12.08.07.00 XEN to KVM Migration | Kapil Kapil | Satish Pothula | Kapil Kapil
VECJAKXAZ |  | GOODYEAR12 | Discovery Complete | (No planning/prep window) | No | Paul Gray | 2020-05-16 21:40:00 | 2020-05-16 23:40:00 | 0 | CC - Firmware - FRO3684, NetApp 5600 CFW Upgrade from 08.30.50.34 to 08.40.40.30 ” | Kapil Kapil |  | Kapil Kapil
VECJ9YQCM | Y Y | BOAD04VA9P11 | Discovery Complete | 2020-05-12 19:30:00 2020-05-26 15:30:00 2020-05-15 19:30:00 2020-05-26 19:30:00 More than 31 days | No | Akhilesh Kasarla | 2020-05-26 19:30:00 | 2020-05-26 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 03/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJ9YQDB | Y | BOAD07VA2 | Discovery Complete | 2020-05-12 19:30:00 2020-05-26 15:30:00 2020-05-15 19:30:00 2020-05-26 19:30:00 More than 31 days | No | Akhilesh Kasarla | 2020-05-26 19:30:00 | 2020-05-26 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 03/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJ9YQA7 | Y Y | BOAD01VA20P14 | Discovery Complete | 2020-05-12 19:30:00 2020-05-26 15:30:00 2020-05-15 19:30:00 2020-05-26 19:30:00 More than 31 days | No | Akhilesh Kasarla | 2020-05-26 19:30:00 | 2020-05-26 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 03/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJ9YQDD | Y | BOAD09VA2 | Discovery Complete | 2020-05-12 19:30:00 2020-05-26 15:30:00 2020-05-15 19:30:00 2020-05-26 19:30:00 More than 31 days | No | Akhilesh Kasarla | 2020-05-26 19:30:00 | 2020-05-26 23:30:00 | 0 | Managed Server - OS Patch - Datamover - Security Bundle using the 03/xx/2020 bundle | Kapil Kapil |  | Kapil Kapil
VECJAN34L |  | DISCOVER28 | Open | (No planning/prep window) | No | Paul Gray | 2020-05-27 15:30:00 | 2020-05-27 17:30:00 | 0 | Firmware - 35FRO3693 Firmware or Microcode BIOS/Baseboard (Dell R730) | Keith Boggs | Kapil Kapil | Keith Boggs
VECJA6SKS |  | DIXONS2800 | Discovery Complete | (No planning/prep window) | No | International CC-Approver | 2020-05-31 17:18:00 | 2020-05-31 19:18:00 | 0 | ICC Prep - 35FRO3677 Firmware or Microcode BIOS/Baseboard - VMS (Will be performed by site team) | Kapil Kapil |  | Jason Parry
VECJA4RTD |  | RSAPROD | Discovery Complete | (No planning/prep window) | No | James Presley | 2020-06-05 15:30:00 | 2020-06-08 17:30:00 | 0 | NPARC - Source RSAPROD DBS/PDE 14.10.05.05 to Target TDICAMRSAPROD02 16.20.43.01 | Kapil Kapil | Yesu Babu Meegada Shikha Saxena Koshal Vyas Bhargavi Mariyala Aruna Paladugu Archi Jain Rajesh Jakkula | Kapil Kapil